## Role Delegation
Developer Group Role Delegation — Byte & Bite (Client: Group 4)
Role | Team Member | Primary Responsibilities (Byte & Bite build) | Also Owns
Project Manager | David | Owns the elicitation process end-to-end: defines session structure, agendas and techniques; keeps the sprint timeline on track; records decisions, risks and outstanding questions after every session; briefs the client on the process at Session 1; manages scope creep against the agreed MVP. | Session minutes; risk log; adaptation document
Lead Developer | Victoria | Owns technical architecture and stack choice (with written justification); breaks epics into tasks and assigns them; ensures DB, backend and frontend integrate each sprint; runs technical reviews before each client session. | Tech stack justification; DB schema; GitHub repo structure
ITBA (+ QA support) | Matthew | Leads requirements elicitation in sessions; drafts and maintains the BRD; produces UML diagrams (use case, sequence, class/ERD extensions); translates elicited requirements into user stories for the backlog; supports QA with acceptance-criteria definition. | BRD; UML diagrams; user story backlog
QA | Nicole | Defines acceptance criteria per user story; tests each sprint increment against functional and non-functional requirements; specifically verifies privacy/anonymity thresholds and causal-caveat displays behave as specified; maintains the test log. | Test plan; test log; privacy/safeguard verification checklist

## Timeline & Deliverables
Byte & Bite — 6-Week Agile Delivery Timeline (Developer Group)
Note: agenda for each Tuesday session is planned and led by this group (the Developers), since Group 4 is our client for this product.
Sprint | Dates | Client Session | Sprint Goal | Key Deliverables | Primary Owner | MVP?
Sprint 0 | Mon 21 – Mon 21 Sep | — | Internal prep before first client contact | Session 1 agenda + question list prepared; SA&D methodology chosen and documented (this group's process charter); GitHub repo initialised; draft backlog template ready | Project Manager
Sprint 1 | Tue 22 – Mon 28 Sep | Session 1 (22 Sep) | Understand the concept; establish the foundation | BRD v1 (draft, from concept-note walkthrough); Use Case Diagram v1; initial product backlog / user stories; low-fidelity wireframes (dashboard + 1 feature screen); session 1 minutes incl. open questions log | ITBA
Sprint 2 | Tue 29 Sep – Mon 5 Oct | Session 2 (29 Sep) | Confirm requirements; design foundations | BRD v1.1 (client sign-off); ERD extended for Byte & Bite fields; tech stack decision + written justification; hi-fidelity wireframes for all 4 features; sprint 3–6 backlog prioritised with client | Lead Developer
Sprint 3 | Tue 6 – Mon 12 Oct | Session 3 (6 Oct) | MVP Increment 1: foundation + easiest feature live | Synthetic dataset v1 generated and loaded; working DB + backend skeleton; Rush Hour Radar (peak/quiet detection) functional on synthetic data; basic dashboard shell | Lead Developer | Y
Sprint 4 | Tue 13 – Mon 19 Oct | Session 4 (13 Oct) | MVP Increment 2: privacy-safe benchmarking | Fair Comparison Score implemented with peer-grouping + minimum-group-size anonymity threshold; privacy/safeguard mechanisms verified by QA; client review of MVP so far | ITBA + QA | Y
Sprint 5 | Tue 20 – Mon 26 Oct | Session 5 (20 Oct) | MVP Increment 3: causal caveats + forecasting | Honest Results Checker (context/confounder warnings) implemented; Demand Forecast (baseline trend/seasonal model) implemented; integration testing across all 4 features | Lead Developer + QA
Sprint 6 | Tue 27 Oct – Mon 2 Nov | Session 6 (27 Oct) – final review | Harden, document, prepare for handover | Bug fixes from QA test log; README + Adaptation Document drafted; deployment/config script tested by someone outside the team; demo script + presentation prep; final client sign-off | QA + Project Manager
Submission | Tue 3 Nov, 23:59 | — | Deliver | Git bundle submitted; README + Adaptation Document in repo; SCARF self-evaluation submitted (individual) | Project Manager
Presentation | Thu/Fri 5–6 Nov | — | Present to lecturers | Live demo of working system; peer evaluation completed | Whole team
Legend:
Green 'MVP' rows = the minimum working slice needed for a demonstrable product if time runs short.

## Client Session Schedule
Client Engagement Session Schedule — Byte & Bite
Session | Date | Goal (Developer-led) | Pre-Session Prep (us) | Ask of Client (Group 4) | Output After Session
1 | 22 Sep | Walk through concept note; resolve ambiguities; agree process | Prepare full question list (see agenda); explain agile process + session rules to client | Come ready to explain each feature in their own words; bring examples if any exist | BRD v1 draft; open-questions log
2 | 29 Sep | Confirm requirements; prioritise MVP order | Draft BRD v1.1 + backlog from Session 1 answers; propose build order for sign-off | Review and sign off BRD; confirm which 2 features matter most if scope must shrink | Signed-off BRD; prioritised backlog
3 | 6 Oct | Review MVP Increment 1 (Rush Hour Radar) | Have a working demo ready, even if rough | Feedback on peak/quiet detection accuracy and dashboard usability | Change requests logged
4 | 13 Oct | Review MVP Increment 2 (Fair Comparison Score) | Have peer-benchmarking demo ready with anonymity threshold visible | Confirm the grouping logic feels fair; approve privacy approach | Sign-off on privacy mechanism
5 | 20 Oct | Review MVP Increment 3 (Honest Results Checker + Demand Forecast) | Have both features demoed together | Feedback on caveat wording and forecast usefulness | Final change requests
6 | 27 Oct | Final review before submission | Full system demo, README draft ready | Final sign-off; confirm nothing critical is missing | Client sign-off for submission